# Phase 1 MVP Sprint Plan — BO2026

Product: InstantLead AI (AI Lead Response System)
Sprint: Phase 1 MVP (Weeks 1-2)
Dates: February 17 – February 27, 2026
Target: Working MVP with 6 core features
Status: 🟡 In Progress

## 🎯 Sprint Objectives

Deliver a functional MVP that can: 1. Receive leads via Follow Up Boss (FUB) webhook 2. AI-qualify leads using Claude 3.5 (intent, budget, timeline, urgency) 3. Send instant SMS responses via Twilio (< 30 seconds) 4. Display leads in an agent dashboard (Next.js + shadcn/ui) 5. Sync data back to FUB CRM 6. Include Cal.com booking links for qualified leads

## 👥 Team Assignments

| Agent Role | Owner | Responsibilities |
| --- | --- | --- |
| Product Executive | @Leonida (You) | Sprint coordination, blocker resolution, daily reports |
| Development | @DevAgent | Backend APIs, integrations, AI engine, database |
| Design | @DesignAgent | Dashboard UI refinement, component implementation |
| Marketing | @MarketingAgent | Landing page deployment, pilot recruitment |
| Analytics | @AnalyticsAgent | Tracking setup, metrics dashboards, PostHog config |
| QC/Compliance | @QCAgent | Compliance review, ToS/Privacy updates, consent flows |

## 📅 Day-by-Day Breakdown

### Week 1: Foundation & Core Pipeline

#### Day 1 — Monday, Feb 17

Theme: Environment Setup & Architecture

| Time | Task | Owner | Deliverable | Dependencies |
| --- | --- | --- | --- | --- |
| 09:00 | Sprint kickoff meeting | Product | Agenda, goals, communication plan | - |
| 10:00 | Supabase project setup | Dev | Database project, initial schema | - |
| 10:00 | Vercel project setup | Dev | Next.js 15 project, CI/CD pipeline | - |
| 11:00 | Environment variables config | Dev | .env.local template, secrets mgmt | Supabase, Vercel setup |
| 12:00 | Lunch break | - | - | - |
| 13:00 | Twilio account verification | Dev | Twilio SID, Auth Token, phone number | ⏳ A2P pending |
| 14:00 | FUB API key request | Product | API key request submitted | - |
| 14:00 | n8n Railway deployment | Dev | Self-hosted n8n instance | Railway account |
| 16:00 | Database schema design | Dev | schema.sql with tables: Lead, Message, Agent | Supabase ready |
| 17:00 | EOD Standup (15 min) | Product | Blocker report, Day 2 plan | - |

End of Day 1 Success Criteria: - [ ] Supabase project created with RLS policies - [ ] Vercel project deployed (hello world) - [ ] n8n instance running on Railway - [ ] Environment variables documented in 1Password/Vault

#### Day 2 — Tuesday, Feb 18

Theme: Lead Intake Pipeline

| Time | Task | Owner | Deliverable | Dependencies |
| --- | --- | --- | --- | --- |
| 09:00 | FUB webhook listener | Dev | POST /api/webhooks/fub endpoint | FUB API key |
| 10:00 | Lead parsing & validation | Dev | Parse FUB payload, validate required fields | Webhook endpoint |
| 11:00 | Market detection (US/CA) | Dev | Auto-detect market from phone/location | Lead parsing |
| 12:00 | Lunch break | - | - | - |
| 13:00 | Lead deduplication logic | Dev | Check existing leads by phone/email | Database schema |
| 14:00 | Consent validation | Dev | Check opt-in status before processing | DNC/compliance list |
| 15:00 | Lead creation in DB | Dev | createLead() service function | All above |
| 16:00 | Webhook logging | Dev | Webhook event log table for debugging | - |
| 17:00 | EOD Standup | Product | Blocker report, Day 3 plan | - |

End of Day 2 Success Criteria: - [ ] Webhook endpoint receives and logs FUB events - [ ] Leads are parsed, validated, and stored in Supabase - [ ] Duplicate detection working - [ ] Consent validation prevents processing DNC leads

#### Day 3 — Wednesday, Feb 19

Theme: AI Qualification Engine

| Time | Task | Owner | Deliverable | Dependencies |
| --- | --- | --- | --- | --- |
| 09:00 | Vercel AI SDK setup | Dev | Install @ai-sdk/anthropic, configure Claude | - |
| 10:00 | Qualification prompt v1 | Dev | Claude prompt for intent/budget/timeline/urgency | - |
| 11:00 | AI qualification service | Dev | qualifyLead() function with Claude API | Prompt ready |
| 12:00 | Lunch break | - | - | - |
| 13:00 | Response generation | Dev | Generate personalized SMS from qualification | AI qualification |
| 14:00 | Qualification result storage | Dev | Store AI analysis in Lead table | DB schema |
| 15:00 | Confidence scoring | Dev | AI confidence score (0-100) for human handoff | - |
| 16:00 | Qualification tests | Dev | Unit tests for 5 lead scenarios | Jest/vitest |
| 17:00 | EOD Standup | Product | Blocker report, Day 4 plan | - |

End of Day 3 Success Criteria: - [ ] Claude qualification working end-to-end - [ ] AI extracts: intent, budget, timeline, location, urgency - [ ] Personalized SMS generated for each lead - [ ] Confidence scores assigned - [ ] Unit tests passing

#### Day 4 — Thursday, Feb 20

Theme: SMS Response System

| Time | Task | Owner | Deliverable | Dependencies |
| --- | --- | --- | --- | --- |
| 09:00 | Twilio SDK integration | Dev | Twilio client setup, SMS send function | Twilio credentials |
| 10:00 | SMS template selection | Dev | Logic to select template based on qualification | SMS templates |
| 11:00 | Message personalization | Dev | Inject lead name, agent name, Cal.com link | Qualification data |
| 12:00 | Lunch break | - | - | - |
| 13:00 | SMS sending endpoint | Dev | POST /api/sms/send with Twilio | All above |
| 14:00 | Delivery status tracking | Dev | Webhook for Twilio delivery receipts | - |
| 15:00 | Message history logging | Dev | Store all sent messages in Message table | DB schema |
| 16:00 | Compliance: STOP handling | Dev | Auto-unsubscribe on STOP keyword | Compliance review |
| 17:00 | EOD Standup | Product | Blocker report, Day 5 plan | - |

End of Day 4 Success Criteria: - [ ] SMS sent via Twilio within 30 seconds of lead creation - [ ] Delivery tracking working (sent/delivered/failed) - [ ] All messages logged with timestamps - [ ] STOP keyword handling implemented

#### Day 5 — Friday, Feb 21

Theme: FUB CRM Integration & Week 1 Wrap

| Time | Task | Owner | Deliverable | Dependencies |
| --- | --- | --- | --- | --- |
| 09:00 | FUB API client setup | Dev | FUB API wrapper with auth | FUB API key |
| 10:00 | Lead sync to FUB | Dev | Update FUB lead with AI qualification data | FUB client |
| 11:00 | Event logging in FUB | Dev | Log “AI Response Sent” events in FUB | - |
| 12:00 | Lunch break | - | - | - |
| 13:00 | Status update sync | Dev | Sync lead status changes back to FUB | - |
| 14:00 | Error handling & retries | Dev | Retry logic for failed FUB API calls | - |
| 15:00 | Week 1 integration testing | Dev | E2E test: Lead → AI → SMS → FUB sync | All features |
| 16:00 | Week 1 demo prep | Product | Demo script, test leads ready | - |
| 17:00 | Week 1 Review | All | Demo, blocker discussion, Week 2 planning | - |

End of Week 1 Success Criteria: - [ ] Complete pipeline: FUB webhook → AI → SMS → FUB sync - [ ] E2E test passes with sample leads - [ ] All data properly synced between systems - [ ] Week 1 demo completed successfully

### Week 2: Dashboard, Booking & Polish

#### Day 6 — Monday, Feb 24

Theme: Agent Dashboard — Lead Feed

| Time | Task | Owner | Deliverable | Dependencies |
| --- | --- | --- | --- | --- |
| 09:00 | Next.js dashboard layout | Design + Dev | Dashboard shell with navigation | - |
| 10:00 | Lead Feed component | Design + Dev | List view with lead cards | Supabase data |
| 11:00 | Priority badges | Design + Dev | Visual indicators for lead urgency | Qualification data |
| 12:00 | Lunch break | - | - | - |
| 13:00 | Quick actions (buttons) | Design + Dev | Call, SMS, Mark Qualified buttons | - |
| 14:00 | Real-time lead updates | Dev | Supabase realtime subscriptions | - |
| 15:00 | Lead detail view | Design + Dev | Modal/drawer with full lead info | - |
| 16:00 | Responsive mobile view | Design + Dev | Mobile-optimized lead feed | - |
| 17:00 | EOD Standup | Product | Blocker report, Day 7 plan | - |

End of Day 6 Success Criteria: - [ ] Dashboard displays leads in real-time - [ ] Priority badges show AI urgency assessment - [ ] Quick actions work (call/SMS open native apps) - [ ] Mobile view functional

#### Day 7 — Tuesday, Feb 25

Theme: Response History & Analytics

| Time | Task | Owner | Deliverable | Dependencies |
| --- | --- | --- | --- | --- |
| 09:00 | Response history component | Design + Dev | Conversation thread view | Message table |
| 10:00 | Conversation search/filter | Dev | Search by lead name, phone, date | - |
| 11:00 | Basic analytics widgets | Analytics + Dev | Response time, lead volume charts | PostHog setup |
| 12:00 | Lunch break | - | - | - |
| 13:00 | Analytics dashboard screen | Design + Dev | Performance metrics display | Analytics data |
| 14:00 | Export functionality | Dev | CSV export for lead data | - |
| 15:00 | Dashboard settings | Dev | User preferences, timezone, etc. | - |
| 16:00 | Dark mode polish | Design | Final dark mode styling pass | - |
| 17:00 | EOD Standup | Product | Blocker report, Day 8 plan | - |

End of Day 7 Success Criteria: - [ ] Response history shows all AI and agent messages - [ ] Analytics show: avg response time, leads/day, conversion rate - [ ] CSV export working - [ ] Dark mode consistent across all screens

#### Day 8 — Wednesday, Feb 26

Theme: Cal.com Booking Integration

| Time | Task | Owner | Deliverable | Dependencies |
| --- | --- | --- | --- | --- |
| 09:00 | Cal.com self-hosted setup | Dev | Cal.com instance deployed | Server/Vercel |
| 10:00 | Booking link generation | Dev | Dynamic Cal.com links per agent | Cal.com API |
| 11:00 | Booking link in SMS | Dev | Include booking URL in qualified responses | SMS templates |
| 12:00 | Lunch break | - | - | - |
| 13:00 | Booking webhook handler | Dev | Receive booking events from Cal.com | - |
| 14:00 | Update lead on booking | Dev | Mark lead as “appointment” when booked | - |
| 15:00 | Booking confirmation SMS | Dev | Send confirmation with details | - |
| 16:00 | Agent calendar view | Dev | Show upcoming bookings in dashboard | - |
| 17:00 | EOD Standup | Product | Blocker report, Day 9 plan | - |

End of Day 8 Success Criteria: - [ ] Cal.com instance running - [ ] Booking links included in qualified lead SMS - [ ] Bookings update lead status automatically - [ ] Agents see upcoming appointments in dashboard

#### Day 9 — Thursday, Feb 27

Theme: Testing, QA & Pilot Prep

| Time | Task | Owner | Deliverable | Dependencies |
| --- | --- | --- | --- | --- |
| 09:00 | Full E2E test suite | QC + Dev | All 9 E2E tests passing | All features |
| 10:00 | Security audit | QC | Check for exposed keys, SQL injection | - |
| 11:00 | Compliance review | QC | TCPA, CASL, CCPA compliance check | - |
| 12:00 | Lunch break | - | - | - |
| 13:00 | Performance testing | Dev | Load test webhook handling | - |
| 14:00 | Error scenarios testing | QC | Test failure modes, error messages | - |
| 15:00 | Pilot onboarding flow | Marketing | Signup form, welcome email | Landing page |
| 16:00 | Documentation | Product | API docs, setup guide for pilots | - |
| 17:00 | EOD Standup | Product | Blocker report, Day 10 plan | - |

End of Day 9 Success Criteria: - [ ] All 9 E2E tests passing - [ ] Security audit complete (no critical issues) - [ ] Compliance check passed - [ ] Pilot onboarding ready

#### Day 10 — Friday, Feb 28

Theme: MVP Launch & Sprint Review

| Time | Task | Owner | Deliverable | Dependencies |
| --- | --- | --- | --- | --- |
| 09:00 | Final bug fixes | Dev | Critical issues resolved | QA feedback |
| 10:00 | Production deployment | Dev | Deploy to production Vercel | - |
| 11:00 | Monitoring setup | Dev + Analytics | Sentry + PostHog dashboards | - |
| 12:00 | Lunch break | - | - | - |
| 13:00 | Pilot recruitment | Marketing | 5 pilot agents signed up | Landing page live |
| 14:00 | MVP demo recording | Product | Loom demo of full flow | - |
| 15:00 | Sprint retrospective | All | What went well, improvements | - |
| 16:00 | Phase 2 planning | Product | Week 3-4 roadmap | - |
| 17:00 | Sprint Celebration | All | 🎉 | MVP complete! |

End of Sprint Success Criteria: - [ ] MVP deployed to production - [ ] 5 pilot agents recruited - [ ] All monitoring active - [ ] Phase 2 roadmap defined

## 🔗 Dependencies Matrix

| Dependency | Required By | Status | Mitigation if Blocked |
| --- | --- | --- | --- |
| Twilio A2P approval | SMS sending (Day 4) | ⏳ Pending | Use toll-free numbers as temp; test with verified numbers only |
| FUB API key | FUB integration (Day 2, 5) | ⏳ Pending | Use webhook simulator; mock FUB responses |
| Claude API credits | AI qualification (Day 3) | ✅ Available | Fallback to OpenAI GPT-4o if needed |
| Cal.com hosting | Booking links (Day 8) | ⏳ Pending | Use Cal.com cloud free tier temporarily |
| Railway account | n8n hosting (Day 1) | ✅ Ready | Fallback to Render or Fly.io |

## 🚧 Risk Register & Mitigations

| Risk | Impact | Probability | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- |
| Twilio A2P delays | Can’t send SMS to new numbers | High | Use toll-free verified numbers; limit pilot to verified numbers | Dev |
| FUB API key delay | Can’t test real integration | Medium | Build with mock FUB; switch to real when available | Dev |
| AI qualification accuracy | Poor lead quality assessment | Medium | Start with simple rules; iterate prompts daily | Dev |
| Database performance | Slow dashboard at scale | Low | Implement pagination; add indexes early | Dev |
| Third-party outages | Twilio/Claude downtime | Low | Queue messages; retry with exponential backoff | Dev |
| Compliance gaps | Legal risk | Low | QC review on Day 9; conservative opt-in approach | QC |
| Pilot recruitment slow | No users to test | Medium | Marketing starts recruitment Day 1; offer 30-day free | Marketing |

## 📊 Success Metrics (Sprint Level)

| Metric | Target | Measurement |
| --- | --- | --- |
| Feature completion | 100% (6/6) | Checklist tracking |
| E2E test pass rate | 100% (9/9) | Automated test suite |
| Response time | <30 seconds avg | PostHog tracking |
| Lead capture rate | 95%+ | % of leads with AI response |
| SMS delivery rate | 98%+ | Twilio delivery receipts |
| Pilot signups | 5 agents | Marketing tracking |
| Critical bugs | 0 | QA sign-off |

## 📝 Daily Standup Format

Time: 5:00 PM EST (17:00)
Duration: 15 minutes max
Attendees: All agents

Template:

1. What I completed today:
2. What I'm working on tomorrow:
3. Blockers/I need help with:

Product Executive reports to Leonida with: - Sprint burndown status - Blockers requiring escalation - Next day priorities - Any scope changes needed

## 🔄 Change Control

Scope Changes: Any feature additions require Product Executive approval
Timeline Changes: >1 day slippage requires team discussion and mitigation plan
Resource Changes: Agent reallocation must be communicated same day

## 📈 Post-Sprint Phase 2 Preview

| Week | Focus | Key Deliverables |
| --- | --- | --- |
| Week 3 | Pilot Feedback & Iteration | Dashboard improvements, prompt tuning, bug fixes |
| Week 4 | Voice AI (Inbound) | VAPI integration, inbound call handling |

Last Updated: February 16, 2026
Next Review: Daily at 5 PM
Sprint Owner: @Leonida (Product Executive Agent)